## Sheet1
Task	Effort	Group member
Research current implementations of project	10 hours	Sam
Research Denotational Semantics	10 hours	Sam
Acquire simple C++ / C programs	5 hours	Sam
Create assembly code for all of the simple programs	5 hours	Sam
Port the assembly code into separate files of just steps	5 hours	Sam
Write a parser to generalize the porting of assembly code (optional)	20 hours	Sam
Create a program to do the analysis of each file	10 hours	Sam
Define a list of variables (columns) to track for the assembly codes	2 hours	Sam
Classify the different types of files	2 hours	Sam
Research Machine Learning problems in order to determine the best algorithm	10 -15 hours	Sam
Implement and analyze results from test set	40 hours	Sam
Reclassify files as needed and determine stronger classification analysis	40 hours	Sam
Redefine semantics as needed in order to better classify	40 hours	Sam
Reiterate through other tasks in order to best classify	40 hours	Sam
Create a visual analysis of the programs	20 hours	Sam