## Sheet1
Milestones	Task	Date Starting	Date Ending	Milestone End
Initial Research	Research current implementations of project	10/01/17	10/31/17	2017-10-31
	Research Denotational Semantics	10/01/17	10/31/17
Creation of dataset	Acquire simple C++ / C programs	2017-11-01	11/10/17	2017-12-01
	Create assembly code for all of the simple programs	11/10/17	11/15/17
	Port the assembly code into separate files of just steps	11/15/17	11/20/17
	Write a parser to generalize the porting of assembly code (optional)	2017-03-01	2018-04-01
	Create a program to do the text analysis of each file	11/20/17	11/27/17
	Define a list of variables (columns) to track for the assembly codes	11/27/17	2017-12-01
	Classify the different types of files	11/27/17	2017-12-01
Writing of Machine Learning Algorithm to compare documents Writing of Machine Learning Algorithm to compare documents	Research Machine Learning problems in order to determine the best algorithm	2017-12-01	2018-01-01	2018-01-01
	Implement and analyze results from test set	2017-12-01	2018-01-01
Definition of "Functionality"	Reclassify files as needed and determine stronger classification analysis	2018-01-01	2018-02-01	2018-03-01
	Redefine semantics as needed in order to better classify	2018-01-01	2018-02-01
	Reiterate through other tasks in order to best classify	2018-02-01	2018-03-01
Creation of Visual Exploration of files and findings	Create a visual analysis of the programs	2018-03-01	2018-04-01	2018-04-01